Insert Company/Community Logo

Event Management Plan Template and Guidance Notes

| EVENT DETAILS |  |
| --- | --- |
| Name of Event |  |
| Event Contact |  |
| Event location including postcode or grid reference |  |
| Event Type (eg field, village hall ) |  |
| Event Capacity and expected number of attendees |  |
| No of Staff/Volunteers |  |
| Date of Event |  |
| Required Set –up Time |  |
| Required Pack up Time |  |

| Event Manager |  |
| --- | --- |
| Organisation |  |
| Address |  |
| Phone |  |
| Email |  |

Contents

1.	Event management	5

1.1.	Pre Planning	5

1.2.	Event overview	6

1.3.	Licence and application checklist	6

1.4.	Key event management contacts	6

1.5.	Key event contacts – other	7

1.6.	Staffing	8

1.7.	Organisational matrix	9

1.8.	Programme & production schedule	9

1.9.	Run sheet	10

2.	Health and safety	11

2.1.	Your responsibility for health and safety at your event	11

2.2.	Risk assessments and management	12

2.3.	Risk assessments – other contractors	12

2.4.	Security	12

2.5.	Stewarding	13

2.6.	Emergency procedures	13

2.7.	First aid / medical cover	13

2.8.	Electricity	14

2.9.	Fire safety at your event	14

2.10.	Fun fairs and inflatable play equipment	15

2.11.	Temporary demountable structures	16

2.12.	Animals at Events	17

3.	Site considerations	17

3.1.	Site Plan	17

3.2.	Vehicles on site	18

3.3.	Traffic, transport and parking	18

3.4.	Toilets	19

4.	Communications	19

4.1.	Event communications – Surrounding residents	20

4.2.	Event day communications - Audience	20

4.3.	Event day communications – Internal	20

5.	Lost children	21

6.	Licensing	22

6.1.	Premises and TEN (Temporary Events Notice)	22

6.2.	PRS and PPL Licence	22

7.	Insurance	22

8.	Special Effects ( eg fireworks and pyrotechnics, etc)	23

9.	Provision of food	23

10.	Environmental considerations	23

10.1.	Waste management	23

10.2.	Noise	24

10.3.	Drinking Water	24

10.4.	Weather	25

Introduction

The purpose of this document is to provide broad guidance notes for event organisers planning to hold an event . The document also provides sections that should be completed to help you develop a detailed EMP (Event Management Plan).

To use the template, save a new version and complete the sections that apply to your event - marked with a pencil prompt ( and blue text.  Not all sections will apply to all events: you will need to decide which are relevant to your event.  Once you have completed the template, you can delete the guidance text.

Our online event guidance includes information that will be useful when preparing your event management plan. Please take time to read this.

You may also find the Health and Safety Executive’s (HSE) guidance on event safety helpful.

The Purple Guide to Health, Safety and Welfare at Music and Other Events has been drawn up by the Events Industry Forum in consultation with the UK events industry, including representatives from regional and national Government. This has replaced the "Purple Guide" (HSG195) which was originally published by the Health & Safety Executive (HSE). For information on accessing the Purple Guide can be found at thepurpleguide.co.uk .

# Event management

## Pre Planning

The success of any event is always dependent upon adequate pre planning and it is essential that you allow enough lead-time to ensure that your event is a success. By addressing the why, what, where, when and who early in your planning process, it will help you to make informed decisions during the event planning process.

Why – it really is worth asking this question at the very beginning, sometimes you may find that the answer is not immediately obvious. By addressing the why it will help your organising committee establish the core values of your event. Establishing the core values will help you design your event and develop the ‘who’ and therefore ‘what’ elements you should include as part of your event programme.

What – you need to decide what it is that you will present at your event. Your core values will provide direction here. Knowing who your target audience is will help you identify what elements should be at your event. Try to put yourself in the shoes of someone from your target audience, what are their interests, what will attract and excite them at your event.

Where – some things that should be considered when deciding on your event venue include: site area, access, community impact, transport, car parking, ground conditions and existing facilities such as toilets. It is also worth considering your venue in terms of your target audience, is the location accessible to your main target audience?

When – consider your event date in terms of some of the following: other events, day of the week, do your opening times suit your audience and the likely weather conditions at that time of the year.

Who – this is one of the most important points to consider in your pre planning process. Identifying the ‘who’ will come from your ‘why’ and the identification of the core values. Your ‘who’ may also mean you need to give special consideration for facilities such as young children, teenagers, the elderly or disabled.

## Event overview

- Provide a paragraph here that provides an executive summary of the event.

Please keep in mind that you are trying to provide someone who knows nothing about your event with as much information as possible in a succinct paragraph or two.

## Licence and application checklist

- Use the checklist below to record the licences and permissions you have applied for.

| Checklist | Yes | No | N/A |
| --- | --- | --- | --- |
| Temporary Event Notice (TEN) |  |  |  |
| Road Closure Application |  |  |  |
| Permission/Licence to use Council owned Land provide details) |  |  |  |
| Any other licensing requirements (provide details) consents and licences |  |  |  |
| Have you checked if your event requires planning permission? (provide details) |  |  |  |

## Key event management contacts

- Populate the following table with the names, roles, responsibilities and contact details of the key people involved in organising your event.

Any event should always have one person who is ultimately responsible for all aspects of the event. Depending on the nature and scale of the event a number of other people will have key tasks and responsibilities allocated to them, but will report to the event manager.

| Name | Role | Responsibility | Contact (Mbl Pref) & radio channel if radio allocated |
| --- | --- | --- | --- |
| John Williams | Event Manager | Overall responsibility | XXXXXXXXXXX Radio channel 1 |
| Jane Jones | Health & Safety | Risk assessments, legal compliance, fire points, site inspections | XXXXXXXXXXX Radio channel 1 |

## Key event contacts – other

- Populate the below table with all the other key contacts for your event.

You as the event organiser should start collating the details of all people that will have some involvement with your event. This could be event suppliers, stallholders, emergency contacts, council contacts etc.

| Suppliers (marquees, catering etc) |
| --- |
| Organisation | Contact | Service | Contact details | Notes |
| ABC marquees | Mike Evans | Temporary structures | Email and mobile | Price confirmed waiting for written quote |
| Authorities (fire, police, first aid etc) |
| Organisation | Contact | Service | Contact details | Notes |
| North Wales Police | Sgt Steve Smith | On call | Email and mobile | Have briefed on event |
| Artists / Entertainment |
| Organisation | Contact | Service | Contact details | Notes |
| ABC arts | Helen Hughes | Walkabout entertainment | Email and mobile | Require payment on the day |

## Staffing

Over and above the key event management contacts you have documented under section 2.3 please list here the other staff that will be required to deliver your event. It is important that you think carefully about your event and the level of staffing that will be required. It is easy to underestimate how many staff will be required to plan and successfully run your event. Following an event design process and completing a risk assessment will help to ensure that you allocate adequate staff to the event, thus ensuring it is effectively managed and is safe for the public and your staff.

## Organisational matrix

- Create a simple organisational matrix below.

For smaller and community based events an organisational matrix should still be developed. It helps the smooth running of the event if everyone understands the management structure and who is responsible for what. It is also an essential element in your emergency response planning. If an incident occurs it is crucial that your staff, the public and the emergency services understand your chain of command. The below example is a very simple structure, you should highlight the levels of command and the protocols for communication up and down the hierarchy.

The Emergency Services would take overall control in the event of a major incident.

## Programme & production schedule

- Please populate the below production schedules.

It’s important that you produce and document an event day programme; this not only helps your event management on the day but also allows you to promote your programme to your audience prior and during the event.

A production schedule is also an essential element in successful event management, it ensures tasks are done on time and not forgotten, with so much to think about it is easy to forget things if you don’t document each and every task. Regardless of the scale of the event you should document what needs to be done prior, during and after the event to ensure all tasks are carried out in a timely manner. A simple production schedule that can be used is provided below with an example in each.

| Production Schedule XXXXXX event – prior to event day |
| --- |
| Date | Task | Start | Finish | Resources/ who | Notes | In Hand | Complete |
| 20/06/2009 | Pick-up event signage from sign writer | 10am | 12 noon | Van + Bill & Ben | Take cheque for payment | X Van booked |  |
| Production Schedule XXXXXX event – event day |
| Task | Start | Finish | Resources/ who | Notes | In Hand | Complete |
| Stall holders arrive on site | 7am | 9am | Stalls coordinator – Sam | All vehicles off site by 9.30 and no further vehicle movements | X stalls coordinator briefed |  |
| Production Schedule XXXXXX event – post event |
| Date | Task | Start | Finish | Resources/ who | Notes | In Hand | Complete |
| 25/06/2009 | Return generator | 9am | 10am | Van + Tom | Make sure cables go back | X |  |

## Run sheet

- You can use the below table as a template to develop a run sheet for your event.

A run sheet is a useful tool when your event has multiple activities occurring across the day at different locations within the event site. For example you may have a stage, arena area and walkabout entertainment. Therefore it’s important you programme all the activities in a sensible and logical manner to make the event flow for your audience. For example you could programme an arena act to start shortly after a stage act has finished, this gives time for a stage changeover without a total absence of entertainment to keep your audience entertained. Run sheets can be as detailed as seconds for a stage production, however for smaller outdoor events increments of between 5 and 15 minutes usually works well.  An example of a basic run sheet is provided below.

Please note that often a separate stage run sheet should be developed that is in minute increments, this helps to ensure a professional and seamless stage programme is presented.

|  | Stage and arena programme for XXXXX event |
| --- | --- |
| Time | Stage programme | Arena programme | Face painter | Walkabout theatre | Bubble blower | Balloon modeller | other |
| 12:00 | Mayor opening |  | Face painter |  |  |  |  |
| 12:05 |  |  |  |  |  |  |  |
| 12:10 |  |  |  |  |  |  |  |
| 12:15 | Changeover | Bike demo |  | Walkabout 1 | Bubble blower |  |  |
| 12:20 |  |  |  |  |  |  |  |
| 12:25 |  |  |  |  |  |  |  |
| 12:30 | Dance performance |  |  |  |  | Balloon modeller |  |
| 12:35 |  |  |  |  |  |  |  |
| 12:40 |  |  |  |  |  |  |  |
| 12:45 |  |  |  |  |  |  |  |
| 12:50 |  |  |  |  |  |  |  |
| 12:55 |  |  |  |  |  |  |  |

# Health and safety

## Your responsibility for health and safety at your event

The Health and Safety at Work Act 1974 is the primary piece of legislation that covers health and safety at work. Even if you are a community organisation with no employees it is still your responsibility to ensure that your event and any contractors are operating legally and safely. To this, it is essential that you address the following headings to ensure that you have taken all steps that is reasonably practical to ensure your event is safe and complies with all health and safety law and guidelines.

## Risk assessments and management

- Please include a copy of your completed risk assessment.

The risk assessment process in not an option when planning an event, it is an absolute necessity.  It is important that a risk assessment is not just something you do because it is a legal requirement; it is the single most important tool to ensure you cover all health, safety and planning aspects of your event. A risk assessment is a ‘fluid’ document that should be developed early, constantly monitored, adjusted and shared widely with internal and external stakeholders.

The first step in the process is to develop a risk register, do this with your planning group and brainstorm every identifiable risk. Each identified risk will then be dealt with via the risk assessment template. You must include the fire risk within this assessment.

## Risk assessments – other contractors

Please list here all other contractors associated with your event that you will need to collect copies of their risk assessments. Some examples could be a fun fair ride, face painter or walkabout performer. Remember that you as the event organiser hold ultimate responsibility for any element of the event you contract in.

## Security

Most events, although not all, will require some professional security. The main purpose of security and stewarding is crowd control and it will be your risk assessment that will identify what your security requirements will be. When assessing the security needs of your event give consideration to the following; venue location, date, operating times, target demographic, planned attendance numbers, fenced or open site etc.

Document your security plan here. Security at events must be SIA (Security Industry Authority) registered. More information is available at http://www.sia.homeoffice.gov.uk/Pages/home.aspx

## Stewarding

In addition to your own organisations staffing requirements you will also need to consider stewarding requirements.

Document your stewarding plan here. Some key points to consider when developing your plan are: Your risk assessment will help you identify your requirements Stewards require training and briefings to ensure they are fully aware of their duties and responsibilities You must ensure that you develop a communications plan for all staff, including stewards as they need to understand how they can cascade information or report incidents during the event Give consideration to; venue location, date, operating times, target demographic, planned attendance numbers, fenced or open site etc

## Emergency procedures

Please document here what emergency procedures you will have in place for your event. Once again your risk assessment should help you document your procedures. Think about what you will do if a fire occurs, where on the site will you evacuate people? How will you communicate this instruction to your audience? Who will take responsibility for these decisions? What systems do you have in place to contact emergency services? It is important that you document your procedures and communicate this with all your event staff, contractors and volunteers, as well as making the emergency services aware of your event. Emergency procedures will always include definitions, i.e. when does an incident become major and therefore the management of the incident is handed over to the police.

## First aid / medical cover

Please document here what first aid and or medical cover you will have at your event. The Wales Ambulance Service Trust can provide you with a Special Event Risk Assessment.

## Electricity

If you are including electrical supply as part of your event please document the details here. Temporary electrical installations are subject to the same standards and regulations as permanent electrical installations and must comply with the general requirements of the Electricity at Work Regulations 1989. Any event that has electrical supply included must have a competent electrician sign-off the installation prior to the event starting.

## Fire safety at your event

You must address the area of fire safety for your event. As stated under 3.2 Risk Assessments and Management you need to include the risk of fire in your event risk assessment.

Please confirm here that you have addressed the fire risk in your event risk assessment. Also document how you have addressed the key areas of the fire risk assessment process highlighted below: Identify the fire hazards, i.e. sources of ignition, fuel and oxygen Identify people at risk within and surrounding your site and those at highest risk Evaluate the risk of a fire occurring and evaluate the risk to people should a fire occur Remove or reduce fire hazards and remove or reduce the risks to people Consider the following: detection and warning, fire fighting, escape routes, signs and notices, lighting, maintenance Recording significant findings and action taken Prepare and emergency plan Inform and instruct relevant people, provide training Keep assessment under review and revise where necessary Useful resources for fire safety planning include: http://www.communities.gov.uk/publications/fire/firesafetyassessment Fire Safety Risk Assessment – open air events and venues (downloadable from above website)

## Fun fairs and inflatable play equipment

If you plan to have bouncy castles, rides or a fun fair at your event you must carry out a number of checks and collect a range of documentation.

Please include here any inflatable play equipment you intend to have at your event. Points you will need to address before approval is granted for any piece of inflatable play equipment are: Is the operator conforming to the PIPA Scheme? Have they carried out the daily checks on the equipment as required by EIS7 When was the equipment last fully inspected? Will you get full instructions on its SAFE operation? Has the inflatable a PIPA tag? Do you have a copy of the current PIPA test certificate for this equipment If it is set it up with the blower unit at 1.2 metres distance will it still fit on my site? Is the equipment clearly marked as to its limitations of use (max. user height etc.)? Are you a member of a relevant association (AIMODS, NAIH or BIHA)? (Check this against the relevant web site listing (See Participating Organisations) Do they have £5 million Public Liability Insurance? Further guidance on inflatable play equipment is available at http://www.hse.gov.uk/entertainment/fairgrounds/inflatables.htm. Please include here any rides or fun fairs you intend to have at your event. Points you will need to address before approval is granted for any ride or fun fair are: Any stand-alone ride or rides that are part of a fun fair must be part of the ADIPS (Amusement Device Inspection Procedures Scheme) scheme The operator must provide you with a copy of their In-Service Annual Inspection papers and copy of these must be provided to the Events Team The operator must also confirm in writing that that adhere and operate under the HSG175 Fairgrounds and Amusement Parks – Guidance on Safe Practice Further information is available on the HSE website in regards to the ADIPS scheme at http://www.hse.gov.uk/entertainment/fairgrounds/adsc.htm

## Temporary demountable structures

The use of temporary demountable structures at events is an area that is broad and complex. For a small event it may simply be some market stalls and a marquee. Larger events and festival may include stages, grandstands, lighting towers, gantries, site offices etc. Depending on the scale and types of structure, different authorities will be required to be involved in the approval process. If structures are planned to be in place for extended periods of time then planning permissions may be required. Larger temporary constructions would require independent engineers to sign-off structures before they can be used. So you can see that this is an area that requires careful consideration.

Please provide a detailed list of all temporary structures you plan to bring onto your event site. Include what procedures you will follow to ensure all structures are supplied by a competent contractor. All suppliers will need to supply you with a copy of their public liability and employee insurance certificates All suppliers will need to provide you with relevant risk assessments and method statements relating to the product they are supplying for your event Suppliers will provide a signed hand over inspection once the structure is completed to say that it is safe and ready for use You need to consider all other health and safety aspects relating to any temporary structure

## Animals at Events

You must provide copies of all relevant licences and registration documents for each animal with your event application plan.

You are responsible for the welfare of the animals under the Animal Welfare Act 2006.  This includes the animals’ transport, housing, food and how they are displayed to the public.

Please provide a detailed list of all animals you plan to bring onto your event site. Include copies of all relevant licences and registration documents for each animal.

# Site considerations

## Site Plan

- Please include a copy of your site plan within this document or as separate attachment.

A site plan must be submitted for each and every event. As this template has been designed to assist smaller event organisers we do not expect you to supply a site plan of a standard that we would anticipate from a larger professional event organiser, however the more accurate and detailed the plan the better. It will help you execute the site build and production elements of your event.

Your site plan should include the following:

| Placement of all temporary structures | All other site infrastructure |
| --- | --- |
| Any fencing or barriers | Generator or power sources |
| Power supply runs (cables) | Entry and exit points |
| Emergency exits and assembly points | First aid points |
| Information point | Lost children’s point |
| Vehicle entry points/emergency vehicle access. | Event décor, i.e. flags, banners etc |

Be aware that you may want to create two versions of a site plan, one that you would use at the site on the day to provide event participants with information and another version that is purely for your management team. Accurate site plans are very helpful when you are doing the site build as you are able to clearly direct people when they arrive on-site to their correct position. Site plans are also a useful tool in the event design process as you can plan how people will enter the site, how people will interact with the site and how people will move about the site.

## Vehicles on site

Please outline here what you vehicle policy is for you event site. Points to consider when developing your vehicles on site policy: As part of your emergency planning (and included on your site plan) you should have clearly marked emergency ingress and egress routes. Ideally this should be a sterile route however this may not always be possible and you therefore need a procedure in place for the safe ingress and egress of emergency vehicles. What vehicles will need to access the site for your event? What vehicles will need to remain onsite throughout your event and which will be off-site before the event opens? Are there any vehicles that will need to move on the site during your event? It is strongly recommended that you avoid the need for this, however if it is needed you should have a rigid procedure in place and ensure that all people involved in your event are fully briefed on the protocol.

## Traffic, transport and parking

Many smaller community events will have limited impact on traffic and parking, however it is still important that you give this consideration when planning your event. Larger events can have significant impacts on local traffic and transport and will require extensive risk assessments and detailed plans dealing specifically with traffic and transport. It is important that through your risk assessment you consider traffic, transport and parking no matter what scale your event is.

Outline any traffic, transport or parking plans you have in place for your event. Points to consider when developing your plans: How will your target audience travel to your event? Consider the various transport links around the event site, and how these can be promoted to your audience as a way to get to your event. Are you proposing any road closures? If so contact PCC Highways to apply for a road closure, be aware that road closures require a minimum of 6 weeks lead time and in all cases the more notice provided the better.

## Toilets

You are required to provide adequate toilets facilities for you event attendees, staff and contractors.

- Please outline here your planned toilet provisions for your event based on your expected numbers and gender split.

Be conscious that you will need to provide disabled facilities and separate sanitary facilities for caterers.

Further guidance is available in the Purple Guide and BS 6465-1:2006+Amendment 1:2009.

# Communications

The importance of communications when planning and delivering an event is paramount. You need to consider three main areas of communication when developing your event.

- Communicating with your planning team pre event to ensure all people are aware of all what is being proposed. It is also essential that you communicate your event plans to the residents and businesses in the surrounding area, the earlier the better.

- Communications on the day of the event, ensuring that there is a clear communications plan in place and that all stakeholders are familiar with the plan. You also need to make sure that you have the practical tools to make the communication plan work on the day, this could include radios, mobile phones, runners (staff to run errands and messages) and a public address system.

- Audience communication needs to be considered to make the visitor experience enjoyable and seamless. Elements here could include flyers, site plans, signage, public address system, stage schedules, MC’s and information points.

## Event communications – Surrounding residents

Document here how you are going to communicate your event plans to surrounding residents and businesses

## Event day communications - Audience

Document here what plans you have in place for communication with your audience on the day, take note of point 3 above.

## Event day communications – Internal

Document here what plans you have in place for your event day communication for event staff and emergency services, both on site and off site. Key points to consider when developing your plan are: Ensure that under 2.3 Key Event Management Contact you list phone contact details and radio channel details if radios are being used Ensure that via your organisation matrix (2.6) all people working on your event understand the chain of command and therefore who they will contact should they need to report an incident or cascade information Your communications plan needs to be developed taking into consider the organisational matrix and the emergency response plan

# Lost children

Please document here what your lost children’s policy and procedures are. You must ensure that you develop a lost children’s policy and make all event staff and volunteers familiar with the procedures and policy. Some important points to consider when developing your policy are: Identify arrangements for the ‘safe’ care of children until such time that they can be reunited with their parent/s or guardian There should be a clearly advertised point for information on lost children Lost children should never be left in the care of a sole adult, always ensure that there are at least two adults that have the appropriate DBS (Disclosure and Barring Service) checks in place. If a lost child is found and reported to one of the event staff a message should be communicated to all event staff as per the communication plan (radio, phone, in person to event control point) that a ‘code word’ at ‘location’. Two staff should then remain with the child at this point for a period of 10 minutes to allow for a possible quick reunification. If after 10 minutes there has been no reunification then the child should be taken to the designated lost children’s point by two members of staff. If possible this point should be adjacent to your event control point or the first aid/medical area. All incidents need be logged, ensuring all details are recorded. The CRB checked staff should try to ascertain a description of the child’s guardian, their name, mobile number if known and a description. The child and the parent/s guardian should not be reunited until a match has been established. To this if a parent comes to the lost children’s point claiming they have a lost child they must provide a signature and identification along with a description of their child, this could include age, clothing, hair colour, height etc. If there is any reluctance from the child to go with the adult then you should inform the police. Once a lost child incident has been resolved you must inform all staff that the ‘code’ has been resolved. Complete the report and log.

# Licensing

## Premises and TEN (Temporary Events Notice)

If your event is including any licensable activity, please provide details here.

## PRS and PPL Licence

Live and recorded music at one-off events does require a licence with.

Please provide details on any recorded or live music you plan for your event.

# Insurance

All event organisers must hold public liability insurance to the value of £5 million. You must also ensure that any contractors that you are engaging also hold public liability insurance and any other appropriate insurance, i.e. product liability, employee insurance.

Please confirm that you hold public liability insurance to the minimum value of £5 million. You will also need to ensure that you hold copies of all contractors relevant insurance and that copies can be provided upon request

# Special Effects ( e.g. fireworks and pyrotechnics, etc.)

Please provide details of any special effects for example fireworks/ pyrotechnics/ lighting displays. A separate plan to the site plan outlining fall out areas/firing areas/ spectator areas etc. should be provided. Copies of risk assessments from contractors should be examined and included.) Detailed guidance on arranging a display can be obtained on the Health and Safety Executive website and Explosive Industry Group website.

# Provision of food

Document details here of any catering and or provision of food you plan to provide at your event. Please note that all details of any catering concessions should be listed under 2.4 Key Event Contacts – Other. You should ensure that food businesses are registered.

# Environmental considerations

## Waste management

It is essential that your event has a waste management plan in place and that it is carried out.

How will you keep the site clear of waste? Will this be done by stewards or volunteers?

How you will manage waste during and after your event, including details of bins, skips, recycling and litter picking?

Document your waste management plans for your event here.

## Noise

There are a number of ways in which people can be affected from a noise nuisance and these can occur at any time of the day, but most notably in the evening as background noise levels reduce. It is strongly recommended that you inform local residents of your event and leave them with a contact number which they can call you on to discuss any issues which they may have regarding your event.

Noise at your events can come from many different sources for example from recorded music, live music stages, fun fairs and public address systems. You therefore need to consider all potential sources of significant noise which could create a nuisance and put relevant control measures in place to prevent creating a noise nuisance.

Please document what elements of your event have the potential to cause noise nuisance and what plans you have in place to mitigate this. Points to consider: Selection of location for your event Larger events that have a music stage will always have to employ a professional sound engineer and they must liaise with the Public Protection service to establish agreed sound levels Residents should be provided with a event day contact from your organisation that can be contacted on the day should they wish to raise a noise complaint

## Drinking Water

Please document your water supply provision:

## Weather

Severe weather and event cancellation

Consider any weather conditions which may lead your event being cancelled and how you will manage this.

How will you let people know if the event has to be cancelled?

Do you need insurance coverage for cancellation reasons such as thunderstorms, water logged ground etc?

Is there any flood risk, e.g. field liable to flood and create difficulty for traffic leaving?  How will you handle this, e.g.  provision of 4x4 vehicle assistance, agreement with land owner concerning damage to the ground, possible mud on roads etc?

How will your event management team decide if weather conditions are too risky for your event to go ahead?

Please document your severe weather and event cancellation policy and procedures here.

# Text boxes

Event Manager

Safety Manager

Volunteer Manager

Artist Manager

Stewards

Volunteers

Production Manager

Stage Manager

Stage Crew

Security

Production Staff

Emergency Services